# Veld — Execution Plan (Version 4)

Project: Veld — a contract-first, multi-stack API code generator Module: github.com/Adhamzineldin/Veld Plan version: 4 Supersedes: Version 3 (docs/EXECUTION_PLAN_v3.md), Version 2, Version 1 Duration: 16 weeks, divided into 6 phases Team: 5 members — 4 implementing, 1 documentation Cadence: tasks assigned weekly; every week ends with a checkpoint

## 1. What This Version Changes

Version 3 organised the project into six two-week sprints. Version 4 keeps the same scope discipline but restructures delivery around six phases with weekly task assignment and a weekly checkpoint, and adds three things Version 3 did not cover:

| New in Version 4 | Where |
| --- | --- |
| A stabilisation phase that comes first — audit, prioritise and resolve every existing error before any new work begins | §4 (Phase 1) |
| Language and runtime version support — version detection, compatibility testing, and a maintained compatibility matrix across all non-EOL versions | §5 (Phase 2) |
| User-facing command standardisation — the CLI surface made consistent and professional | §8 (Phase 5) |
| Weekly assignment and weekly checkpoints replacing two-week task blocks | §10, §11 |

Everything Version 3 established that you did not change is carried forward unaltered: no new emitters, no new features, frozen-not-deleted tiers, and the registry and plugin programmes.

## 2. Decisions and Assumptions

### 2.1 Confirmed by you

| Decision | Value |
| --- | --- |
| Frontend adapters (5) | typescript, react, vue, angular, svelte |
| Language version support | All actively supported (non-EOL) versions of every officially supported language and runtime, with version detection, compatibility testing, and a maintained compatibility matrix |
| Documentation member | Works the full 16 weeks; receives no weekly implementation tasks |

### 2.2 Assumed — stated openly, each with a one-line change path

These four were not settled. I have taken the default carried from Version 3 in each case rather than block the plan. Say the word on any of them and the change is local — no phase boundary moves.

| # | Assumption | If wrong |
| --- | --- | --- |
| A1 | Backend adapters (5) are node-ts, python, go, java, rust | Swap java → csharp in §6.1 and reassign Member 3's Phase 3 weeks. Nothing else moves. |
| A2 | Rust remains exclusively Member 4's, per your original instruction | If Rust may be shared, Member 4 absorbs a registry or plugin slice in Phases 4–5. |
| A3 | Duration is 16 weeks, with Phase 6 acting as the buffer | A shorter run drops Phase 6 first, then compresses Phase 3. |
| A4 | Weekly assignment replaces the two-week task rule from Version 3 | Revert to the v3 sprint grid; the phase structure survives either way. |

## 3. Phase Overview

| Phase | Weeks | Theme | Exit condition |
| --- | --- | --- | --- |
| P1 | 1–2 | Stabilisation — audit, prioritise, resolve all existing errors | Full build and test suite green on every installed toolchain; defect register closed to P0/P1 |
| P2 | 3–4 | Version & Compatibility — detection, testing, matrix | Every generated project declares its supported runtime range; compatibility matrix published and CI-enforced |
| P3 | 5–10 | Adapters — 5 backends (W5–W7), 5 frontends (W8–W10) | All ten adapters compile clean across their full version matrix |
| P4 | 11–12 | Registry — correctness, performance, reliability | Registry meets §7.3; measured performance targets met |
| P5 | 13–14 | Plugins & Commands — plugin system, CLI standardisation | Both plugins tested and packaged; CLI surface consistent |
| P6 | 15–16 | Hardening, buffer & release | Definition of done (§12) satisfied from a clean clone |

Phases are project-level themes. Members work in parallel within each phase — the week-by-week assignment in §10 is the authoritative statement of who does what.

## 4. Phase 1 — Stabilisation (Weeks 1–2)

"Audit, prioritize, and resolve all current Veld errors and issues."

### 4.1 Blocking finding: three toolchains are missing

Checked on the development machine on 2026-08-26:

| Toolchain | Status | Consequence |
| --- | --- | --- |
| Node / npm | ✅ installed | — |
| Python | ✅ installed | — |
| Java | ✅ JDK 25 (Adoptium) | — |
| PHP | ✅ 8.4 | — |
| Go | ❌ not installed | go build ./... and go test ./... cannot run. Veld is written in Go — the project cannot be compiled or tested at all. |
| Rust / cargo | ❌ not installed | The Rust adapter's output cannot be compile-verified. |
| .NET | ❌ not installed | The C# adapter's output cannot be compile-verified. |
| TypeScript | ⚠️ present only inside an unrelated project's node_modules | No global tsc; generated TypeScript cannot be checked reproducibly. |

Installing Go is Week 1, Day 1, and it blocks everything else in the plan. Until it is done, no build error, test failure or go vet warning in this repository has ever been observed — the defect register in §4.3 is therefore seeded from static inspection and must be re-derived from a real build in W1.

### 4.2 What the codebase actually looks like

Correcting an impression Version 3 could have left: this project is not untested. It has substantial coverage — with one glaring hole.

| Measure | Value |
| --- | --- |
| Test files | 52 _test.go files across the repository |
| Covered | lexer, parser, validator, loader, config, diff, format, lint, LSP, cache, errors, mock, schema, setup, every backend emitter, every frontend emitter, every tool generator |
| Not covered | internal/server/ — the registry. Zero test files, 1,699 lines. |
| Open code markers | 23 TODO / FIXME / HACK / XXX across internal/ and cmd/ |
| Largest file | cmd/veld/main.go — 4,610 lines, 33 command definitions |

### 4.3 Defect register — seeded categories

Week 1 produces the real register. These are the categories it must cover, each already evidenced:

| ID | Category | Evidence | Priority |
| --- | --- | --- | --- |
| D1 | Build and test cannot run | Go not installed | P0 |
| D2 | Registry wholly untested | No _test.go under internal/server/ | P0 |
| D3 | Open code markers | 23 TODO/FIXME/HACK/XXX — each triaged to fix, ticket, or delete | P1 |
| D4 | Hardcoded runtime versions | 13 sites, §5.2 | P1 |
| D5 | CLI inconsistency | §8.2 | P1 |
| D6 | Registry operability gaps | §7.2 | P1 |
| D7 | Plugin defects | §8.3 — including three commands declared but never registered | P1 |
| D8 | main.go at 4,610 lines | Single file holding 33 commands | P2 |

Prioritisation rule. P0 = blocks other work or ships broken output. P1 = user-visible defect or a correctness risk. P2 = maintainability. Phase 1 closes all P0 and P1. P2 items are scheduled into later phases or the Phase 6 buffer — never silently dropped.

## 5. Phase 2 — Language & Version Support (Weeks 3–4)

"Support all actively supported (non-EOL) versions of every officially supported language/runtime. Add proper version detection and compatibility testing. Maintain a clear compatibility matrix."

### 5.1 The problem in one sentence

Veld currently hardcodes a single version of every runtime, in a single place, with no detection, no configurability, and no test that any other version works.

### 5.2 Every hardcoded version — all 13 sites

| What | Where | Value |
| --- | --- | --- |
| Go module directive | internal/emitter/backend/go/middleware.go:157 | go 1.22 |
| Rust edition | internal/emitter/backend/rust/main.go:208 | edition = "2021" |
| Java (Gradle) | internal/emitter/backend/java/strategy/plain.go:92 | JavaVersion.VERSION_17 |
| Java (Maven) | internal/emitter/backend/java/strategy/spring.go:280–282 | <java.version>17</java.version> + compiler source/target |
| .NET target | internal/emitter/backend/csharp/strategy/aspnet.go:114 | net8.0 |
| .NET target | internal/emitter/backend/csharp/strategy/plain.go:58 | net8.0 |
| CI — Go | internal/generators/cicd/cicd.go:111 | go-version: '1.22' |
| CI — Java | internal/generators/cicd/cicd.go:143 | java-version: '17' |
| CI — Python | internal/generators/cicd/cicd.go:188 | python-version: '3.12' |
| CI — Node | internal/generators/cicd/cicd.go:202 | node-version: '20' |
| Docker — Go | internal/generators/dockerfile/dockerfile.go:86 | golang:1.22-alpine |
| Docker — Rust | internal/generators/dockerfile/dockerfile.go:104 | rust:1.76-slim |
| Docker — Java | internal/generators/dockerfile/dockerfile.go:122,130 | maven:3.9-eclipse-temurin-17, eclipse-temurin:17-jre-jammy |
| Docker — Python | internal/generators/dockerfile/dockerfile.go:169 | python:3.12-slim |
| Docker — Node | internal/generators/dockerfile/dockerfile.go:182,190 | node:20-alpine |

Two silent gaps, worse than the hardcoding. Generated package.json has no engines field and generated Python has no requires-python. Node and Python output therefore declares nothing about what runtime it needs — a user on an unsupported version gets a syntax error, not a clear message.

One live mismatch. The development machine runs JDK 25; the emitters target Java 17. Nobody has verified the generated Java on the JDK actually installed here.

### 5.3 The three deliverables

1 — Version detection. A module that resolves, for each target, the version range the generated code supports, in this precedence:

explicit config  →  detected local toolchain  →  project default (lowest non-EOL)

Generated output then declares that range: engines in package.json, requires-python in Python packaging, the go directive, Java source/target, and Cargo edition + rust-version (MSRV).

2 — Compatibility testing. The compile harness runs each adapter against every non-EOL version in its column, not just one. A version that passes enters the matrix as supported; one that fails enters as a documented exclusion with the reason. No version is ever listed as supported without a passing job.

3 — The compatibility matrix. A generated, CI-updated document — never hand-maintained, because a hand-maintained matrix is wrong within a month.

### 5.4 Indicative version columns

Derived at Week 3 from upstream support calendars — these are indicative and must be re-confirmed in W3, because EOL dates move and this plan should not be the authority on them.

| Runtime | Indicative non-EOL set | Policy |
| --- | --- | --- |
| Node.js | 22 LTS, 24 LTS (+ 20 if still in maintenance at W3) | Test every LTS in support |
| Python | 3.10 – 3.14 | Test every branch receiving security fixes |
| Go | last 3 minor releases | Go supports the last 2; we add one for margin |
| Java | 17, 21, 25 (LTS only) | LTS only — non-LTS releases are explicitly out of scope |
| Rust | current stable + pinned MSRV; editions 2021 and 2024 | MSRV is a declared, tested floor |

Scope note. "All officially supported languages" is read as the five Tier 1 adapters plus the frozen Tier 2 set. Tier 2 adapters (node-js, csharp, php) get a single version column each — enough to keep the compile gate honest, without paying for a full matrix on an adapter that carries no parity promise.

## 6. Phase 3 — Adapters (Weeks 5–10)

### 6.1 The 5 backend adapters, in priority order

Priority is by deployment reach and by how much other work each unblocks.

| # | Adapter | Owner | Why this priority |
| --- | --- | --- | --- |
| 1 | node-ts | Member 1 | The flagship. Its tshelpers type-mapping layer is shared with all five frontends — fixing it fixes six adapters at once. Highest leverage in the project. |
| 2 | python | Member 2 | Largest API-backend population after Node. Pydantic and Flask paths are the most-used non-Node output. |
| 3 | go | Member 2 | Veld's own host language. The team reads it fluently, the toolchain is already required to build the project, and its output is the cheapest to verify. |
| 4 | java | Member 3 | Enterprise reach, and the most recent work in the repository (commit 8703a62 fixed ObjectMapper date handling) — momentum is already there. |
| 5 | rust | Member 4 | Highest per-fix cost — borrow checker and lifetimes make generated-code debugging slower than any other target. Isolated to one member by design so its tail risk cannot spread. |

Frozen at Tier 2, compile-gate only, no parity claim: node-js, csharp, php.

### 6.2 The 5 frontend adapters, in priority order

As you specified. Priority within the set is by dependency, not popularity — typescript must be first because the other four wrap it.

| # | Adapter | Owner | Why this priority |
| --- | --- | --- | --- |
| 1 | typescript | Member 1 | The base SDK. react, vue, angular and svelte all delegate to it — every defect here is four defects downstream. Must be green before the others start. |
| 2 | react | Member 1 | Largest user population; React Query hooks are the most complex wrapper. |
| 3 | vue | Member 3 | Composables — second-largest population. |
| 4 | angular | Member 3 | Enterprise; its DI-based service pattern is the most structurally different wrapper and most likely to hide defects. |
| 5 | svelte | Member 3 | Stores — smallest surface, lowest risk, correctly last. |

All five share one toolchain (tsc), which is what makes a five-adapter phase fit in three weeks.

Frozen at Tier 2: javascript, types-only, kotlin, swift, dart — kept, still generating, still compile-gated, but no parity claim.

### 6.3 Definition of green for an adapter

Identical for all ten, so results are comparable:

- Compiles clean on every version in its compatibility column.

- Passes every parity cell, or carries a written documented-gap.

- Declares its supported runtime range in generated output.

- Ships a worked example — contract in, running service or client out.

- Zero runtime dependencies by default (NON-NEGOTIABLE RULE 1).

## 7. Phase 4 — Registry (Weeks 11–12)

"Fix all current Registry issues. Improve its performance, reliability, and efficiency."

### 7.1 Correctness issues — verified

| Finding | Evidence |
| --- | --- |
| Zero automated tests | No _test.go anywhere under internal/server/; 1,699 lines unverified |
| Migrations not versioned | db/db.go:43 — flat CREATE TABLE IF NOT EXISTS, then ALTER TABLE ... ADD COLUMN IF NOT EXISTS at 124–127. No version table, no ordering, no rollback |
| No rate limiting | server.go — the entire chain is Handler: cors(logger(s.mux)) |
| Permissive CORS | Access-Control-Allow-Origin: *, fixed, no allowlist |
| No health or readiness endpoint | registerRoutes() exposes only /api/v1/... routes |
| Unstructured logging | logger formats "%s %s %s" — no request ID, status or latency |
| Upload bounded in memory only | handlers/packages.go:111 — ParseMultipartForm(32 << 20) bounds memory; the remainder spills to disk. No effective upload cap |
| Oversized handler | handlers/auth.go — 482 lines mixing registration, login, logout, TOTP, email verification |

### 7.2 Performance, reliability and efficiency

New in Version 4. Every target is measured, not asserted — Week 11 begins by establishing a baseline, because "improve performance" is meaningless without a before number.

| Dimension | Work | Target |
| --- | --- | --- |
| Baseline | Load-test publish, download and search; record p50/p95/p99 | A recorded baseline exists before any optimisation |
| Database | Index audit — every column used in a WHERE, JOIN or ORDER BY; eliminate N+1 in org-member and package-version listing | No unindexed query on a hot path |
| Connection pooling | db.go opens a pool with defaults; tune MaxOpenConns, MaxIdleConns, ConnMaxLifetime | Pool sized deliberately and documented |
| Downloads | Package tarballs are served through the process | ETag + Cache-Control; conditional 304 on repeat pulls |
| Reliability | Graceful shutdown exists; add DB retry with backoff on transient failure, and a storage-write failure path that does not corrupt package state | No partial publish survives a mid-write failure |
| Efficiency | Streaming upload handling to replace the memory-bounded multipart parse | Publish memory is bounded regardless of tarball size |

### 7.3 Registry definition of done

Tested handlers · versioned migrations · rate limiting · configured CORS · enforced upload cap · /healthz and /readyz · structured logging with request IDs · API reference · operator runbook · passing end-to-end publish→pull test · measured performance improvement against the Week 11 baseline.

## 8. Phase 5 — Plugins & User Commands (Weeks 13–14)

### 8.1 Command standardisation — the CLI is the product's face

cmd/veld/main.go is 4,610 lines defining 33 commands. The surface has drifted.

### 8.2 Verified inconsistencies

| Finding | Evidence | Fix |
| --- | --- | --- |
| Two names for one concept | --out used by 6 commands, --output by 5 | Standardise on --out; keep --output as a hidden deprecated alias |
| Two near-identical flags | --service-sdk and --server-sdk — one character apart, different meanings | Rename for unambiguity; alias the old names |
| Inconsistent error handling | 29 commands use RunE:, 10 use Run: — those ten cannot return an error idiomatically, so exit-code behaviour differs across the CLI | All commands to RunE: |
| Usage dumped on runtime errors | Only 2 occurrences of SilenceUsage/SilenceErrors across 33 commands — most commands print full help text on an ordinary runtime failure | Set both at root |
| No stdout/stderr discipline | 273 fmt.Println/Printf calls in main.go, 4 os.Exit | Data → stdout, diagnostics → stderr, so output can be piped |
| No consistent machine-readable output | --format appears on only 2 commands | A uniform --json on every command that emits data |
| Monolithic command file | 4,610 lines, 33 commands, one file | Split by command group (P2 — may land in Phase 6) |

Standard applied to every command: consistent flag vocabulary · RunE with proper exit codes · quiet on success, informative on failure · --json where data is emitted · uniform help text with at least one example · no breaking change without a deprecation alias.

### 8.3 Plugin system — verified defects

| Finding | Evidence |
| --- | --- |
| Declared commands never registered | editors/vscode/package.json contributes veld.validate, veld.generate, veld.generateDryRun; activate() at src/extension.ts:1534 registers six providers and zero registerCommand calls. All three fail from the palette |
| Four grammars, one language | Go lexer/parser (authoritative) · 1,676-line TypeScript re-implementation · Kotlin PSI layer · veld.tmLanguage.json. A syntax change must land in four places |
| The LSP server exists, unused | internal/lsp/ is 1,151 lines with a passing lsp_test.go; VS Code re-implements it client-side, JetBrains ignores it |
| PATH assumption | VeldExternalAnnotator.kt:25 — ProcessBuilder("veld", "validate"), no configurable path, no fallback |
| Zero plugin tests | No test source anywhere under editors/ |
| Schema triplicated by hand | scripts/sync-schema.sh copies the canonical schema to two plugins; nothing verifies the copies are current |
| Stale artefact committed | editors/vscode/veld-vscode-0.1.0.vsix checked in while package.json declares 0.2.0 |

Out of scope, deliberately. Migrating VS Code onto internal/lsp/ is the single largest simplification available to this codebase — and it is a feature change, so it is post-v1.0 work (§13), not Phase 5.

## 9. Phase 6 — Hardening, Buffer & Release (Weeks 15–16)

Allocated in priority order: carry-over from any missed weekly checkpoint → P2 defects deferred from Phase 1 → release candidate verified from a fresh clone on a clean machine → defence rehearsal run by someone who did not write the script.

No new adapter, no new feature. The buffer exists to make what is already promised true. Surplus time goes to tests and documentation.

## 10. Weekly Task Assignment

The authoritative schedule. Member 5 does not appear — by your instruction they carry no weekly implementation tasks (§11.2).

| Wk | Phase | Member 1 — Node/TS & web | Member 2 — Python/Go & infra | Member 3 — Java, web frameworks & registry | Member 4 — Rust only | Checkpoint |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | P1 | Audit node-ts + 5 frontends; log defects | Install Go; run full build, go vet, go test ./...; triage every failure | Audit java; read internal/server/ end to end | Install Rust; audit rust adapter | C1 — consolidated defect register, every item prioritised P0/P1/P2 |
| 2 | P1 | Fix P0/P1 in TS surface | Fix P0/P1 in Go/Python surface; triage all 23 TODO/FIXME markers | Fix P0/P1 in Java; write registry current-state assessment | Fix P0/P1 in Rust | C2 — build green, go test ./... green, P0/P1 closed |
| 3 | P2 | Node/TS version policy; add engines to generated package.json | Build the version-detection module; stand up the CI version matrix | Java version policy; verify generated Java on JDK 25 (currently targets 17) | Rust MSRV + edition policy (2021 / 2024) | C3 — compatibility matrix v0 published; non-EOL columns confirmed against upstream calendars |
| 4 | P2 | Wire version declaration into TS/Node output | Add requires-python; make the 13 hardcoded sites configurable | Java source/target from detection, not constants | rust-version (MSRV) in generated Cargo.toml | C4 — every generated project declares its runtime range; matrix CI-enforced |
| 5 | P3 | node-ts to green (priority 1 — unblocks 5 frontends) | python to green (priority 2) | java to green (priority 4) | rust — Serde structs, Axum handlers | C5 — each backend demonstrated against the reference contract |
| 6 | P3 | node-ts across full version matrix; service SDK verified | python matrix; start go (priority 3) | java matrix; ObjectMapper date round-trip tested end to end | rust — services trait, parity cells | C6 — backends green on every supported version, not just one |
| 7 | P3 | node-ts worked example + target guide | go to green + worked example | java worked example + target guide; csharp Tier 2 gate | rust — reqwest service SDK | C7 — all 5 backends meet §6.3; Tier 2 freeze in place |
| 8 | P3 | typescript to green (priority 1 — the base all others wrap) | Tool-generator assertions; php Tier 2 gate | vue to green (priority 3) | rust — worked example | C8 — base TS SDK green; no frontend proceeds until it is |
| 9 | P3 | react to green (priority 2) | Compile harness extended to the full frontend matrix | angular to green (priority 4 — most structurally different) | rust — target guide | C9 — 4 of 5 frontends green |
| 10 | P3 | react matrix; frontend parity review across all 5 | CI matrix consolidation | svelte to green (priority 5) | rust — full version matrix (editions + MSRV) | C10 — all 10 adapters meet §6.3 |
| 11 | P4 | Registry API contract & auth — document every route; decompose auth.go (482 lines); rate limiting; CORS from config | Registry performance baseline — load-test publish/download/search, record p50/p95/p99; index audit | Registry operability — /healthz, /readyz, structured logging with request IDs | rust — hardening against the finished parity matrix | C11 — performance baseline recorded before any optimisation |
| 12 | P4 | Auth handler tests, including negative paths | Versioned migrations + schema_migrations; streaming upload cap; connection-pool tuning; ETag/304 on downloads | SPA review; operator runbook; end-to-end publish→pull test | rust — release verification | C12 — registry meets §7.3; measured gain vs C11 baseline |
| 13 | P5 | VS Code extension — register the 3 missing commands; test suite; remove stale .vsix | CLI standardisation — --out/--output; --service-sdk/--server-sdk; all Run: → RunE:; SilenceUsage | JetBrains plugin — configurable binary path; verify VeldActions.kt; test suite | rust — docs and examples review | C13 — palette commands work in both editors |
| 14 | P5 | Plugin packaging verified via PUBLISHING.md by a second person | stdout/stderr discipline; uniform --json; help text with examples; schema-drift CI gate | Plugin packaging verified; JetBrains schema copy under the CI gate | rust — final matrix confirmation | C14 — CLI consistent; both plugins tested and packaged |
| 15 | P6 | Carry-over + P2 defects | Carry-over; main.go split by command group if time allows | Carry-over + P2 defects | Carry-over | C15 — release candidate cut from a fresh clone |
| 16 | P6 | Release verification | Release verification | Release verification | Release verification | C16 — definition of done (§12) satisfied; defence rehearsed |

### 10.1 Reading the schedule

- Dependencies are real. typescript (W8) precedes react/vue/angular/svelte

because all four wrap it. node-ts (W5) precedes everything because tshelpers is shared. The version-detection module (W3) precedes every adapter phase because adapters must declare ranges they cannot yet compute.

- Member 4 is Rust for all 16 weeks, per assumption A2. The Rust track

is genuinely full: adapter parity, service SDK, worked example, target guide, and the edition-plus-MSRV version matrix, which is the deepest version work in the project.

- Member 2 carries the shared infrastructure — version detection, compile

harness, CI matrix — which is why their adapter load is two backends rather than three.

## 11. Weekly Checkpoints

### 11.1 The protocol

Every week ends with a checkpoint (C1–C16). Thirty minutes, same four questions, every member answers:

- Completed — what was finished, demonstrated, not described.

- Issues — what went wrong, and what is blocked.

- Carry-over — what did not finish, and where it now goes.

- Next — the coming week's assignment, confirmed in writing.

The carry-over rule. Work that does not finish is never silently extended. It is re-planned at the checkpoint with a named owner and a new target week. If it cannot land inside its phase, it moves to Phase 6 explicitly.

Escalation. Two consecutive checkpoints missing the same item triggers a scope decision, not a third attempt — reassign, cut, or demote the adapter to Tier 2.

Evidence. A checkpoint claim of "done" needs a build, a test run, or a generated artefact. Nothing is accepted on assertion.

### 11.2 Member 5 — Documentation

Works the full 16 weeks and receives no weekly implementation task, by your instruction. They attend every checkpoint as recorder, and own:

| Workstream | Content |
| --- | --- |
| Architecture | Pipeline, emitter registry and init() activation, interface hierarchy, strategy pattern, consumes service-SDK model |
| Compatibility matrix | The user-facing publication of §5 — which runtime versions are supported per adapter, and why any is excluded |
| Support matrix | Tier 1 / Tier 2 and the parity matrix, with every documented gap explained in plain language |
| Target guides | One per Tier 1 backend — node-ts, python, go, java, rust |
| CLI reference | Every command, flag and exit code — rewritten against the Phase 5 standard |
| Registry & operations | API reference, operator runbook, deployment and auth-flow diagrams |
| Editor plugins | Setup guide for both, feature comparison, authoritative-grammar statement |
| Defence materials | Slide deck, demonstration script, and the "what we deliberately did not build" section |

Standing constraint. No document may describe a capability that does not exist in the repository, and no component may be presented as more mature than it is. Every technical claim must be verifiable by a reader opening the code.

## 12. Definition of Done

- All P0 and P1 defects closed; P2 items scheduled or explicitly deferred with a reason.

- 5 backend adapters — node-ts, python, go, java, rust — meet §6.3 on every version in their compatibility column.

- 5 frontend adapters — typescript, react, vue, angular, svelte — meet §6.3.

- Tier 2 adapters — node-js, csharp, php, javascript, types-only, kotlin, swift, dart — compile or lint clean; the matrix states no parity is claimed.

- Version support complete — detection implemented, every generated project declares its runtime range, compatibility testing runs on every supported version, and the matrix is CI-generated.

- Registry meets §7.3, including a measured performance improvement against the Week 11 baseline.

- Both plugins meet §8.3 — commands registered, tests passing, packaging reproducible, schema drift CI-gated.

- CLI meets the §8.2 standard — consistent flags, RunE throughout, stdout/stderr discipline, uniform --json.

- CI is green and gating — compile harness, parity matrix and version matrix all block merge.

- Non-negotiable rules hold — zero runtime dependencies by default, framework-agnostic handlers, native fetch.

- Member 5's workstreams complete, every claim verifiable in the repository.

## 13. Risk Register

| # | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Go is not installed, so nothing can be built or tested | Confirmed | Critical | Week 1 Day 1 task, ahead of all other work. Until resolved, no claim about build or test status is admissible. |
| R2 | Rust and .NET missing; TypeScript only in an unrelated node_modules | Confirmed | High | Installed in W1. CI is the authoritative environment; missing toolchains skip with a recorded reason and never report a false pass. |
| R3 | The version matrix multiplies CI cost beyond what is practical | High | Medium | Tier 2 adapters get one column, not a matrix. Full matrix runs nightly and on release branches; pull requests run the lowest and highest supported version only. |
| R4 | EOL dates shift during the project, invalidating the matrix | Medium | Low | The matrix is generated, not hand-written. A version leaving support is a CI change, not a document rewrite. |
| R5 | Supporting the oldest non-EOL version forces compromises in generated code | Medium | Medium | The floor is declared per adapter and tested. If a modern construct is worth more than an old version, the floor rises and the matrix records why. |
| R6 | typescript slips at W8, blocking four frontends | Medium | High | It is scheduled alone in W8 with no competing task. If it slips, svelte (lowest priority) is cut to Tier 2 rather than delaying the phase. |
| R7 | Rust proves harder than one member can carry | Medium | Medium | Decided at C7 (W7), not later: Member 3 joins the Rust track for two weeks and angular/svelte move to Phase 6. |
| R8 | Registry performance work finds no headroom, or regresses correctness | Low | Medium | W11 establishes the baseline before optimising. Any change failing the correctness suite is reverted regardless of its speed gain. |
| R9 | CLI standardisation breaks existing users' scripts | Medium | High | Every renamed flag keeps a hidden deprecated alias. No flag is removed in v1.0 — only deprecated. |
| R10 | Weekly checkpoints degrade into status reading | Medium | Medium | Every "done" claim requires a demonstration. The four questions are fixed and the recorder is Member 5, who is not competing for time. |
| R11 | Phase 1 uncovers more defects than two weeks can absorb | Medium | High | P0/P1 close in Phase 1; P2 defers by design. If P0/P1 alone exceeds two weeks, Phase 3 loses svelte first, then angular. |
| R12 | main.go at 4,610 lines makes CLI standardisation risky | Medium | Medium | Behavioural standardisation (flags, RunE, streams) comes first as P1; the file split is P2 and may land in Phase 6 or after v1.0. |

## 14. Post-v1.0 — Recorded, Not Absorbed

In priority order. Nothing here is attempted during the 16 weeks.

- Migrate the VS Code extension onto internal/lsp/, deleting the 1,676-line client-side re-implementation of a language server the project already owns. Largest single simplification available.

- Split cmd/veld/main.go by command group, if not reached in Phase 6.

- The seven cancelled Version 2 emitter commitments — SolidJS, Ruby, Kotlin backend, Actix strategy, and three service-client promotions.

- Promote a Tier 2 adapter to Tier 1 — csharp is the strongest candidate.

- Generate the plugin grammars from the Go lexer, retiring the four-grammar duplication.

## Appendix A — Ownership

| Component | Owner |
| --- | --- |
| internal/emitter/backend/node/ — node-ts | Member 1 |
| internal/emitter/frontend/typescript/, react/ | Member 1 |
| internal/emitter/tshelpers/ | Member 1 |
| editors/vscode/ | Member 1 |
| internal/emitter/backend/python/, go/ | Member 2 |
| internal/generators/ — all six tool generators | Member 2 |
| Version detection · compile harness · CI matrix | Member 2 |
| cmd/veld/main.go — CLI standardisation | Member 2 |
| Registry data, migrations, performance | Member 2 |
| internal/emitter/backend/java/ | Member 3 |
| internal/emitter/frontend/vue/, angular/, svelte/ | Member 3 |
| internal/server/ — registry operability, programme lead | Member 3 |
| editors/jetbrains/ | Member 3 |
| internal/emitter/backend/rust/ — exclusive | Member 4 |
| docs/ — all documentation and diagrams | Member 5 |

## Appendix B — Checkpoint Index

| ID | Week | Phase | Gate |
| --- | --- | --- | --- |
| C1 | 1 | P1 | Defect register complete and prioritised |
| C2 | 2 | P1 | Build green, tests green, P0/P1 closed |
| C3 | 3 | P2 | Compatibility matrix v0 published |
| C4 | 4 | P2 | Runtime ranges declared; matrix CI-enforced |
| C5 | 5 | P3 | Backends demonstrated against the reference contract |
| C6 | 6 | P3 | Backends green on every supported version |
| C7 | 7 | P3 | All 5 backends meet §6.3 · Rust escalation decision point |
| C8 | 8 | P3 | Base typescript SDK green |
| C9 | 9 | P3 | 4 of 5 frontends green |
| C10 | 10 | P3 | All 10 adapters meet §6.3 |
| C11 | 11 | P4 | Registry performance baseline recorded |
| C12 | 12 | P4 | Registry meets §7.3 with measured gain |
| C13 | 13 | P5 | Palette commands work in both editors |
| C14 | 14 | P5 | CLI consistent; plugins tested and packaged |
| C15 | 15 | P6 | Release candidate cut from a fresh clone |
| C16 | 16 | P6 | Definition of done satisfied |

## Appendix C — Version History

| Version | Structure | Status |
| --- | --- | --- |
| v1 | Role-based division | Superseded — docs/EXECUTION_PLAN_v1.md |
| v2 | Type-system families, expansion-oriented | Superseded — docs/EXECUTION_PLAN_v2.md |
| v3 | Type-system families, six two-week sprints | Superseded — docs/EXECUTION_PLAN_v3.md |
| v4 | Six phases, weekly assignment, weekly checkpoints; adds stabilisation, version support and CLI standardisation | Current |

End of Execution Plan, Version 4.